## Slide 1: The Southeast Asian G@G
Issues for Steering Group discussion
15 September 2016
Zsuzsanna Lonti, OECD
Edwin Lau, OECD
Warren Turner, ADB

## Slide 2: The SEA G@G objectives
Forum for discussion on comparative public sector performance
Build evidence for informed policymaking
Support on-going efforts to improve public sector productivity in the region

## Slide 3: Proposed table of content
1) Fiscal and budgetary context for public services
Public finances (IMF/GFS)
Public employment (OECD/ILO)
Budget practices and procedures (OECD survey)
2) Citizen-driven public services
Digital government (OECD survey)
Open government and open data (OECD survey)
3) Capacity to respond to changing public sector challenges
Strategic Human Resources management (OECD survey)

## Slide 4: How data quality will be ensured ?
Respondent: primarily government officials (experts in areas the surveys cover)
Workshops organized for respondents on survey instruments
Data cleaning guides prepared by the OECD (internal consistency and external checks)
Both OECD and ADB experts will review the data
Country experts will also review the data

## Slide 5: Timeline
2016 | Mid-September | Sea G@G Steering group meeting, Bangkok (Thailand)
 | Early October | 2 Surveys sent to countries: -Strategic HRM -Digital Government Deadline to respond: mid-November
 | Mid-November | 1 survey sent to countries -Open Government Data Deadline to respond: end of December
 | End of December | End of data collection
2017 | January-March | Data cleaning period
 | April | Data shared with experts
 | May | Data shared with countries for final comments
 | June-August | Production of the publication (drafting, editing, formating) TBC: Organization of second Steering group meeting and workshops to finalize data cleaning
 | September | Publication sent to countries for comments
 | October | Production of the country fact sheets
 | November | Official launch of the publication in the region

## Slide 6: OECD contact points
Data collection phase:
  Topic experts
    Guillaume Lafortune (Open Government and Open Data). guillaume.lafortune@oecd.org
    Daniel Gerson (Strategic Human Resource Management). daniel.gerson@oecd.org
    Rodrigo Mejia Ricart (Digital government performance). rodrigo.mejiaricart@oecd.org
Data cleaning phase:
  Alice Lazzati (ADB international consultant) alice.lazzati@nuffield.ox.ac.uk

## Slide 7: Key decision points
Key points | Description | Discussion / Decision
1. Topics covered in the first edition | Agree on a final list of surveys to be conducted in the region in 2016-17 as part of the first SEA G@G edition. Delegates are asked to provide feedback on the usefulness to include additional data collection. | Budgeting practices and procedures Open Government and Open Data Digital government performance Strategic Human Resource Management Other:_________________________
2. Topic of the policy chapter | Discuss possible topic(s) for the introductory policy chapter of the SEA G@G (e.g. public serice delivery, public sector productivity). | 
3. Country participation | Discuss countries’ participation in the SEA G@G initiative. Delegates are asked to indicate their willingness to participate in the SEA G@G exercise, to designate officials for Steering Committee and contact(s) to respond to the OECD questionnaires. | 
4. Timeline | Agree on a timeline towards publication and launching of the SEA G@G. | 
5. Next Steering group meeting | Discuss the timing and location for the next Steering Group meeting. |